## Slide 1
Richmond Rising
Collaborative Stakeholder Committee (CSC)
December 4, 2024

## Slide 2
Every first Wednesday of the month 6:00 – 8:00 pm.
In-person Attendance: Nevin Community Center 598 Nevin Ave, Richmond, CA 94801
Virtual Attendance: https://ci-richmond-ca-us.zoom.us/webinar/register/wn_gx8xwknptcutbnefzdbv1w
Phone Attendance: (669) 900-6833, or (669) 444-9171 Webinar ID: 976 6319 9451
All Committee members and members of the public must abide by the Community Agreements
Meeting Information

## Slide 3
While Richmond Rising seeks to strengthen the economy, improve public health and the environment – particularly in the Iron Triangle, Santa Fe and Coronado Neighborhoods, we do so with the awareness that we occupy unceded Huichin and Karkin Ohlone territory.
We acknowledge that land theft of indigenous homelands, and the dismantling of indigenous sovereignty, was done to advance colonization.
We acknowledge that capitalism and white supremacy are branches of colonization that have persisted throughout hundreds of years of oppression, are alive today, and contribute to keeping Black, Indigenous, and all other People of Color from thriving.
We further acknowledge that this country’s political economy and social institutions were built on the forced labor of African people on stolen land through violent, systematic abduction from their homelands and enslavement over hundreds of years.
Land Acknowledgement

## Slide 4
We further acknowledge the exploitation of immigrant and refugee communities as modern forms of cheap and disposable labor are regularly carried out on stolen land.
Thus, we acknowledge that we have been impacted and harmed by these histories and experiences imposed on our ancestors and communities. We further uplift the shared struggle among Black, Indigenous, and All People of Color.
We also acknowledge that indigenous people continue to live here, steward the land, and resist settler colonialism.
We conclude that our Land acknowledgement is an active and evolving statement and process. It requires us to recognize historical injustices and invites us in to be active participants in our collective healing.
Land Acknowledgement

## Slide 5
The City of Richmond and 6 local organizations (together known as ‘Richmond Rising’) received $35 million to bring health, economic, and environmental benefits to the Iron Triangle, Santa Fe, and Coronado neighborhoods.
Richmond Rising is supported by the California Strategic Growth Council’s Transformative Climate Communities Program.
Richmond Rising

## Slide 6
Provides guidance on project implementation and holds us accountable in reaching our goals
Can make recommendations, provide input, and assist Project Leads in implementing project activities
Does not have final decision-making authority
Project Leads must consider recommendations from the Committee and members of the public
Collaborative Stakeholder Committee

## Slide 7
This is the space for members of the public to provide public comment on items that are not included in the agenda.
Public Comment Not on the Agenda

## Slide 8
Members to review and approve previous meeting minutes
Review and Approve Previous Meeting Minutes

## Slide 9
Each partner will share up-to-date financials and grant expenditures to date for each project and this will be shared with the Committee and the public.
Project Status Reports

## Slide 10
Work completed since last meeting:
  CSC Meeting: Scheduled, coordinated, and currently facilitating CSC meeting #10, including translation, refreshments, and childcare.
  Invoices and Reports:
      Submitted Invoice 7 for months of August and September 2024, in process of responding to SGC comments.
      Calendar for Invoice #8 was sent to partners last week.
    Year 1 Annual Progress Report. Completed and submitted to SGC. Waiting for comments.
    Submitted amendments and modifications request for TA Agreement.
    Met regularly with all project partners and SGC and DOC grant managers.
    Coordinated tour with SGC staff and partners to Richmond Rising project locations on November 14th.
    Attended 2nd Climate Health Promoters Graduation.
    Presented Annual Report to City Council on November 19th in collaboration with partners.
    Attended meeting with NCS, Pogo Park, CSW and residents on December 3rd.
Total expenditures reported to date: $214,646.21
Remaining budget: $479,029.45
Planned work in the next ~two weeks:
  Get approval from SGC for Progress Report and Invoice #7.
  Get reviews from SGC for Annual Report.
Grantee

## Slide 11
Work completed since last meeting:
  Held biweekly coordination meetings between consultant team (CSW) and city staff.
  Hosted Neighborhood Complete Streets town hall at Nevin Community Center on November 16th, from 12:00 to 2:00pm.
  Met with residents, Pogo Park, CSW and City staff to review all feedback received on Neighborhood Complete Streets project.
Total expenditures reported to date: $ 9,752.89
Remaining budget: $ 5,171,420.26
Planned work in the next ~two weeks:
  Continue working on project design.
  Coordinate meeting with residents, Pogo Park, CSW and City staff to review updated plans.
  Updated ITO indicators request.
Neighborhood Complete Streets

## Slide 12
Work completed since last meeting:
  TPL review of 30% level design cost estimate of construction
  Design team / TPL / City review of community feedback from the site walk
  Attendance/Participation in Strategic Growth Council tour of TCC projects
  Attendance/Presentation at Richmond City Council meeting
  Attendance at Climate Health Promoters project presentations
Total expenditures reported to date: $ 42,512.01
Remaining budget: $ 4,773,641.59
Planned work in the next ~two weeks:
  Continued design work and engagement planning
  Permitting coordination work
Richmond Wellness Trail

## Slide 13
Work completed since last meeting:
Presented our project to TCC and fellow TCC Partners
Presented at City Council Meeting - Richmond Rising Annual Report
Paid planning fees.
Total expenditures reported to date: $ 116,775.68
Remaining budget: $ 2,344,276.31
Planned work in the next ~two weeks:
  Assisting in coordination with 18th Annual MLK Day event on Monday, January 20, 2025
eBike Lending Library

## Slide 14
Work completed since last meeting:
  17 completed projects/ 54 total in our pipeline
  No new reports since last meeting
Total expenditures reported to date: $ 334,046.56
Remaining budget: $ 6,632,649.35
Plannned work in the next ~two weeks:
  n/a
Resilient Homes

## Slide 15
Work completed since last meeting:
  Developing and implementing training modules for Water Catchment systems in anticipation of 2025 installations.
  6 sites prepped for installation, 1 drip irrigation system completed (next installation scheduled for 12/4)
Total expenditures reported to date: $ 174,570.02
Remaining budget: $ 1,506,133.76
Planned work in the next ~two weeks:
  Water Catchment Trainings to develop crew skills.
  Continued installation of free drip irrigation and laundry-to-landscape systems for Richmond homeowners.
Basins of Relations

## Slide 16
Work completed since last meeting:
  Participated in SGC walk-through in Nov.
  Continued canvassing for project tree planting
  Continued coordination for MLK Day of Service in Jan
  Total trees planted – 86 TCC trees, 82 CalFire trees (match)
Total expenditures reported to date: $ 102,596.45
Remaining budget: $ 985,416.30
Planned work in the next ~two weeks:
  Complete invoicing and reporting period (Oct/Nov)
  Canvassing project area for tree adoptions
  Hire new crew member in Jan. 2025
Bosque del Barrio

## Slide 17
Work completed since last meeting:
  Permitting application submitted to the City of Richmond
  Tour of TCC Projects with SGC included the ADA Garden
Total expenditures reported to date: $ 46,611.62
Remaining budget: $ 908,432.38
Planned work in the next ~two weeks:
  Pay for permit, if approved
  Contruction cost estimates
  Construction schedule based on cost estimates
ADA Accessible Garden

## Slide 18
Work completed since last meeting:
  Completed 4th Fruit Tree Lovers Newsletter draft
  Started the implementation of our intake forms to tree care recipients. Allowing the team to better inspect the trees
Total expenditures reported to date: $ 84,984.14
Remaining budget: $ 1,083,229.49
Planned work in the next ~two weeks:
  Begin preparing for the Annual Fruit Tree Giveaway in Spring 2025
  Update the list of trees to order
  Prepare for Winter Apprentice Program by buying tools and making
  sure forms and documents are up to date.
Orchard for ALL!

## Slide 19
Work completed since last meeting:
  Graduated the 2nd cohort of Climate Health Promoters – November 16th
  Finished another 6-week session of HEAT classes with LifeLong Medical – November 27th
  Filled remaining spots for our produce delivery with project area residents
Total expenditures reported to date: $ 397,306.52
Remaining budget: $ 2,841,565.48
Planned work in the next ~two weeks:
  Plan and execute a Veggie Rx photoshoot for the 2nd phase of our Veggie Rx
  website
  Continue to plan and schedule Climate Friendly Diet workshops/events for 2025
Veggie Rx

## Slide 20
Work completed since last meeting:
  TODAY presented to ECIA Transportation Committee and was recommended to receive funding for continuing operation of the Bike Share system for the next 6-8 months.
Total expenditures reported to date: $ 456669.79
Remaining budget: $ 542309.42
Planned work in the next ~two weeks:
  Monthly meeting with City staff and TODAY staff to coordinate work.
E-Bike Share

## Slide 21
Work completed since last meeting:
  Youth Fellow Project Manager: Has sent over finalized onboarding documents to TCC coordinators for review from the City of Richmond's legal time.
  Youth Fellow Project Manager: Created 3 different versions of the Youth Fellow Program Outreach Flyer and submitted to TCC coordinator for approval and feedback on the design.
  City has submitted a Request for Legal Opinion to complete the review,
Total expenditures reported to date: $ 116,600.14
Remaining budget: $ 2,449,432.59
Planned work in the next ~two weeks:
Youth Fellow Project Manager: Continue reviewing feedback and editing modules and training material for final review.
Youth Fellow Project Manager: Will continue with recruitment for Youth Fellows.
City will print flyers provided by Youth Fellow Manager for engagement.
City will coordinate ITP indicator collection on community engagement.
Community Engagement Plan

## Slide 22
Work completed since last meeting:
  Worked on the scope of the Bay Area Future Housing Fellow program.
  Continued to review the ADU Toolkit permitting suite.
  Finalized a contract for the Small Business Building Pilot Program (Facade Improvement), with City Council approval anticipated in late December 2024/early January 2025.
  Finalized a contract for the Events and Marketing Consultant to support the Buy Local Campaign, with City Council approval anticipated in late December 2024/early January 2025.
  Finalized a contract for the Buy Local Software Platform, with City Council approval anticipated in late December 2024/early January 2025.
Total expenditures reported to date: $ 119,464.36
Remaining budget: $ 562,171.26
Planned work in the next ~two weeks:
  Bay Area Future Housing Fellow starting on January 22nd, 2025.
Displacement Avoidance Plan
Notes: The levying of taxes for DRPBID is applicable to many parcels in the downtown area. The money goes to improving the Downtown area and is also the budget for Richmond Main Street Initiative.

## Slide 23
Work completed since last meeting:
  GRID Alternatives: Solar Instructor preparation including attending trainer shadowing at affiliate office. Continued build out of lab space.
  City hosted the Workforce Development Planning Session with Glen Price Group Consultants.
Total expenditures reported to date: $33,563.02
Remaining budget: $ 1,400,244.72
Planned work in the next ~two weeks:
  GRID Alternatives: Continued build out of lab space. Share solar training marketing materials with TCC partners for recruitment efforts
  City will be providing ITP information.
  City staff will be meeting with Glen Price Group to finalize Place Based Workforce Development Plan.
Workforce Development and Economic Opportunity Plan (WDEOP)

## Slide 24
Project lead for City of Richmond
Project lead for GRID Alternatives
Project lead for Groundwork Richmond
Project lead for Rich City Rides
Project lead for Trust for Public Land
Project lead for UC Berkeley
Project lead for Urban Tilth
Roll Call

## Slide 25
Work completed since last meeting:
  Gathered all Year 1 data from project partners (Thank you everyone for taking the time to fill out our forms!)
    WDEOP outstanding (expected 12/16)
    Bosque del Barrio outstanding
  Began draft the comprehensive Year 1 Report (First Draft due on January 15, 2025. Final due March 15, 2025)
    Ran CARB Analyses, created project maps (tree canopy, completed project installations)
Total expenditures reported to date: $ 0
Remaining budget: $ 1,070,000
Planned work in the next ~two weeks:
  Finalize first draft of the report
Indicator Tracking Plan

## Slide 26
Report out on any community questions or comments received, including responses
Report on Public Comments & Questions

## Slide 27
Place-Based Workforce Development Strategy: Findings and Recommendations Presentation
Spanish Climate Health Promoters Program
CSC Resident Nominations
Committee Business Items for Discussion

## Slide 28
Findings and Recommendations Presentation
Place-Based Workforce Development Strategy

## Slide 29
Overview of recent program and graduation
Spanish Climate Health Promoters

## Slide 30
Review and vote on community seat nominations
CSC Resident Nominations

## Slide 31
Agenda Requests for Next Meeting

## Slide 32
CSC Members, members of the public, and other partners or organizations are encouraged to share information or announcements related to upcoming events, projects, or programs in the Project Area
General Announcements

## Slide 33
CSC Partners might want to register to table at this event.
2025 Education Fair CCWC

## Slide 35
Meeting Adjourned
Thank You!
Questions? Comments?
Please reach out at tcc@ci.richmond.ca.us