## Slide 1: New Councilmember Orientation - City of Richmond State Audit
Background
State Audit Recommendations:
  Recommendation 1 through 3
  Recommendation 4, 5
  Recommendation 6, 7
  Recommendation 8 through 11
Questions

## Slide 2
Background
0
3
The State Auditor’s local audit program identifies and supports local government agencies that might be at high risk based upon analysis of the City’s audited financial statements.
The audit was initiated in May 2022 and was completed and published on November 10, 2022.
  During the audit process, the State Auditor held meetings with City staff members to review and discuss many aspects of the City’s financial management procedures and protocol. In compliance with the State Auditor’s request, City staff members provided complete access to the City’s financial data and systems
The State Auditor formalized eleven recommendations.
City is required to provide updates to the State Auditor every six months (May and November).
  Next update is due in May 2025
Notes: Andrea Miller

## Slide 3
State Audit Recommendations
0
3
Number | Description | Time Frame | Corrective Action Plan | November 2024 Update/ Status
1 | To help ensure that Richmond maintains appropriate reserves for times of fiscal uncertainty, city staff should, by June 2023, review Richmond's reserve policy to determine whether a higher reserve target is appropriate. As part of the review, staff should consider all the factors the Government Finance Officers' Association (GFOA) recommends for setting a reserve target. Once that review is complete, city staff should present proposals to the city council for modifying the city's policy. | 6/30/2023 | Schedule City Council review/consideration of updated General Fund reserve policy in March 2023 for implementation in the Fiscal Year (FY) 2023-2024 Budget, for adoption by June 2023. | Completed per June 2023 Supplemental Update. “Staff presented GFOA best practices to the City Council on May 2, 2023, with the first draft budget for FY23-24. Based on the GFOA best practices, on June 27, 2023, the City Council adopted a revised Cash Reserve Policy (see Attached, Cash Reserve Policy)”
2 | To decrease the risk that Richmond will deplete its reserves, city staff should, by June 2023, present to the city council a list of proposed budget actions that would help ensure balanced budgets and eliminate projected deficits. | 6/30/2023 | Present contingent, long-term budget balancing options with the FY 2023-2024 proposed budget, by June 2023. | Completed per June 2023 Supplemental Update. “City Council adopted FY2024-25 budget on June 24, 2024. The City Council adopted a balanced budget for Fiscal Year 2023-2024 on June 20, 2023.”
3 | Richmond should include multiple scenarios in its financial projections, including scenarios with potential additional risks, such as economic downturns or recessions, and how the city would continue to fund its operations under those circumstances. | On Going | Present expanded 5-year financial projection with the FY 2023-2024 Proposed Budget, by June 2023. | Completed per June 2023 and June 2024 Supplemental Updates. “The City staff presented a multiple scenarios forecast to the City Council on June 6, 2023. “

## Slide 4
State Audit Recommendations (Continued)
0
3
Number | Description | Time Frame | Corrective Action Plan | November 2024 Update/Status
4 | To ensure that Richmond is able to fund its retirement-related costs, city staff should, by June 2023, propose to the city council a specific policy regarding funding of its pension trust fund for this purpose. Staff should report to the city council on estimated long-term savings from increasing its direct payments to Cal PERS compared to investing the same amounts in its pension trust fund. Staff members should use this information to inform their recommendations related to funding targets for the pension trust fund and should consider recommending that the council increase the city's payments directly to CalPERS. | 6/30/2023 | Schedule City Council review/consideration of updated Pension funding policy in March 2023 for implementation in the FY 2023-2024 Budget, for adoption by June 2023. | Completed per June 2023 Supplemental Update. “GovInvest presented a Pension Funding PowerPoint presentation at the May 16, 2023, City Council meeting and NHA Advisors presented a PowerPoint presentation on CalPERS Unfunded Accrued Liability Cost Management Strategies at the June 6, 2023, City Council meeting. Based on these presentations the City Council adopted a new Pension Funding Policy.”
5 | To improve the city's ability to pay other post-employment benefits, Richmond should, by June 2023 and annually thereafter, implement a policy identifying funds, such as surpluses or one-time revenues that should be contributed to the OPEB trust fund. Staff should conduct an annual analysis to determine whether any funds available to the city are applicable under the city's policy and should present a proposal to the city council to apply those funds to the trust fund. | 6/30/2023 | Schedule City Council review/consideration of updated OPEB funding policy in March 2023 for implementation in the FY 2023-2024 Budget, for adoption by June 2023. | Completed per June 2023 Supplemental Update. On June 27, 2023, City Council adopted a revised OPEB Funding policy.

## Slide 5
State Audit Recommendations (Continued)
0
3
Number | Description | Time Frame | Corrective Action Plan | November 2024 Update/Status
6 | To mitigate the costs of increasing salaries, the city should perform a workforce analysis by June 2024. Based on the results of the analysis, the city council should consider eliminating vacant positions that it deems no longer necessary. Additionally, the city should assess its need for each vacant position before it seeks to fill the positions and eliminate any positions that it does not need. | 6/30/2024 | The City is issuing a Request for Proposal for a professional firm to conduct a formal workforce analysis. While the City evaluates the professional firms that replied to the Request for Proposal, the City will do an annual analysis of funded positions proposed by departments during the annual budget process, starting with the FY 2023-24 budget, by June 2023. | Completed per June 2024 update. “Staff originally brought the results of the RFP to perform a workforce analysis to the City Council on May 2, 2023. Due to the large volume of agenda items, the RFP was awarded to Raftelis to perform the Workforce Analysis and the contract was approved by the City Council on May 23, 2023.”
7 | To ensure compliance with federal requirements, Richmond should dedicate the resources necessary to provide records needed for an independent auditor to complete all outstanding single audits of the housing authority within the next fiscal year. To comply with existing legal obligations, Richmond should make available sufficient resources to enable the Housing authority to resolve all past due requirements of the recovery agreement and to meet the remaining deadlines in a timely manner by January 2024. | 1/1/2024 | Identify and assign resources to complete Housing Authority Single Audit backlog by June 30, 2023. Identify and assign resources to complete Housing Authority Recovery Agreement actions by January 2024. | Resources have been provided per May 2023 Update. “Audit completion is in progress. (See Recommendation #8)”

## Slide 6
State Audit Recommendations (Continued)
0
3
Number | Description | Time Frame | Corrective Action Plan | November 2024 Update/Status
8 | To define Richmond's responsibility related to the housing authority, Richmond should immediately enter into a written agreement with the housing authority defining each entity's financial responsibilities and draft plans to resolve past tax liabilities and prevent unnecessary new liabilities. | 2/28/2023 | Draft and Schedule City Council consideration of Housing Authority Administration Agreement by February 2023. | Completed per June 2023 Supplemental Update. “On June 27, 2023, City Council approved a written agreement between the City and the Richmond Housing Authority.”
9 | To ensure that Richmond is receiving the best value when entering into contracts, city staff should immediately begin documenting that they are following the contracting requirements in the city's municipal code and contracting policies for all contracts. | 6/30/2023 | Draft and implement Contract Compliance Documentation processes by June 2023. | Completed per May 2023, and June 2024 updates. “City staff conducted an assessment of training materials to ensure compliance with contracting requirements in the City's Municipal Code and contracting policies. Staff prepared training programs to help employees develop the knowledge and skills to ensure compliance.”
10 | To reduce potential errors and omissions by city staff members when contracting for goods and services, by January 2023 Richmond should require its finance department to create a comprehensive checklist of required documentation for contract files that other departments must follow when conducting procurements. | 6/30/2023 | Draft and implement Contract Compliance Checklist by June 2023. | Completed per May 2023 and June 2024 Updates. “City staff compiled comprehensive checklists that are being utilized in reviewing and approving all contracts to ensure that proper procurement procedures and adherence to applicable City policies is being followed.”
11 | To ensure that city fees appropriately cover the cost of providing services, by June 2023, Richmond should determine a cost-effective frequency for updating its fee schedule to reflect all allowable costs, including adjusting fees for inflation as appropriate. Richmond should then revise its municipal code as necessary. | 6/30/2023 | Review and update the Fee Schedule policy for City Council consideration and update of Municipal Code as needed by June 2023. | Completed per June 2023 and June 24 Supplemental Updates. “On June 6, 2023, the City Council adopted an ordinance revising the Master Fee Schedule to annually (rather than quarterly).”

## Slide 7
Thank you!
Questions?